## CSCI 495 Schedule Fall 2017

TODO:

* We will eventually get:
  + Canvas class setup
  + Syllabus and such will be placed there.
* GIT
  + Signup for GitHub account (use your school email)
  + Git Portfolio
  + All work done in this class will need to be checked into GitHub as you do it
    - Weekly / Daily checkins
    - Project Source Code
    - Reports
    - PPT
  + Will share with me…
* Presentation (Travel Thur Nov 9 - Present Friday Nov 10, 2017 in Gatlinburg, TN)
  + About 15 min - group presentation
  + Plus lots of weekly practice presentations
* Tech Reports
  + Project Proposal (1-2 page)
    - Kickstarter Style
      * What it is going to be and how great it is going to be
    - Describe the Phases 0 - 6 and who will be responsible for what
      * Phase 0 - Project Proposal
      * Phase 1 - Rough Working Prototype of core part
      * Phase 2 - Supporting Parts added
      * Phase 3 - Whole System Integration
      * Phase 4 - Cleanup of Whole System
      * Phase 5 - Cleaned and Ready for Presentation
      * Phase 6 - Future Work
  + Project Abstract (.5 - 1 page)
    - Will have early deadline ??? to submit this for the conference
  + Group Report - Primary
    - Summary of the project, and its phases, what you did, etc.
    - Will have template
  + Individual Report
    - Summary from your individual point of view of how the project and team work went
  + Conference Report
    - Summary of 3 other talks (non UTM)
      * Different Sessions
* Poster
  + Will have PPT template
* Resume
  + Resume
  + Linkedin
  + GitHub Portfolio
* LaTex
  + Final Report
* Weekly TPS Reports and Git Checkins
  + Progress Reports & Git Checkins
  + Formal Meeting Schedule

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Week | Date | Phase / Sprint | Details |  |
| 1 | Aug 29 (Tu) | 0 | First day of class - Syllabus & Course Overview |  |
| Aug 31 (Th) | Have Project Trackers Filled Out... |  |
| 2 | Sep 5 (Tu) | Phase 0 - Project Proposal - Due   * Project Proposal (1-2 page)   + Copy Google Doc link to project tracker   What will your rough prototype do? |  |
| Sep 7 (Th) | 1 | Phase 1 - Present and report on  Rough Working Prototype of core part  What supporting parts will be added?   * Abstract Due (.5-1 page) |  |
| 3 | Sep 12 (Tu) |  |
| Sep 14 (Th) |  |
| 4 | Sep 19 (Tu) | 2 | Presentation Practice 1 Begins - Rough Slides |  |
| Sep 21 (Th) |  |  |
| 5 | Sep 26 (Tu) | Phase 2 - Supporting Parts finished |  |
| Sep 28 (Th) | 3 | Round 2 of Practice Presentation  Each group will need to do a 5 - 10 min pres  What parts will be added? How will they be integrated? |  |
| 6 | Oct 3 (Tu) |  |  |
| Oct 5 (Th) | Phase 3 - Whole System Integration finished  **ABSTRACTS DUE TO BOB THIS DATE** |  |
| 7 | Oct 10 (Tu) | 4 | Round 3 of Practice Presentation  Each group will need to do a 10-15 min pres |  |
| Oct 12 (Th) | Abstracts must be submitted Oct 11 |  |
| 8 | Oct 17 (Tu) | FALL BREAK |  |
| Oct 19 (Th) | Phase 4 - Cleanup of Whole System |  |
| 9 | Oct 24 (Tu) | 5 | Final Round 4 of Practice Presentations  Each group will need to do a 15 min pres |  |
| Oct 26 (Th) |  |  |
| 10 | Oct 31 (Tu) |  |  |
| Nov 2 (Th) | Phase 5 - Cleaned and Ready for Presentation |  |
| 11 | Nov 7 (Tu) |  |  |  |
| Nov 9 (Th) |  | TRAVEL TO ACM CONFERENCE GATLINBURG |  |
| Nov 10 (Fr) |  | PRESENT AT ACM |  |
| 12 | Nov 14 (Tu) |  |  |  |
| Nov 16 (Th) |  |  |  |
| 13 | Nov 21 (Tu) |  | Group Reports and Individual Reports and Posters |  |
| Nov 23 (Th) |  | HOLIDAY - THANKSGIVING |  |
| 14 | Nov 28 (Tu) |  |  |  |
| Nov 30 (Th) |  |  |  |
| 15 | Dec 5 (Tu) |  |  |  |
| Dec 7 (Th) |  |  |  |
|  |  |  |  |  |

|  |  |
| --- | --- |
| **Important dates:** |  |
| August 28 | Day and Evening Classes Begin |
| September 1 | Last day to Add, Last day to drop with no record |
| September 4 | Holiday - Labor Day |
| October 13 | Mid-Term Progress Reports Due 8:30am |
| October 20 | Last day to drop, Part of term 1 |
| October 14-17 | Fall Break |
| Nov 13-21 | Advising & Early Registration |
| Nov 9-10 | ACM Conference |
| Nov 22-26 | Thanksgiving Holiday |
| Dec 7 | Commencement Practice |
| Dec 8 | Last Day of Classes / Fall Classes End |
| Dec 9-15 | Final Exams |
| Dec 16 | Fall Commencement |